## Gantt Chart
Lineless – Digital Token Management System ¦ Project Gantt Chart (Jan – Apr 2026)
VBS NUMBER | TASK TITLE | OWNER | START | PHASE 1 – Project Conception & Design | [7 empty] | PHASE 2 – Development, Integration & Delivery
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
|  |  |  | Jan 1-7 | Jan 8-14 | Jan 15-21 | Jan 22-28 | Jan 29-Feb 4 | Feb 5-11 | Feb 12-18 | Feb 19-25 | Feb 26-Mar 4 | Mar 5-11 | Mar 12-18 | Mar 19-25 | Mar 26-Apr 1 | Apr 2-8 | Apr 9-15 | Apr 16-22 | Apr 23-30
Phase 1: Project Conception & Design
1.1 | Project planning & requirement analysis | Team | W1-2 | bar: PHASE 1 – Project Conception & Design Week 1 to PHASE 1 – Project Conception & Design Week 2
1.2 | Tech stack selection (Flutter, Flask, Firebase) | Team | W2-3 | bar: PHASE 1 – Project Conception & Design Week 2 to PHASE 1 – Project Conception & Design Week 3
1.3 | System architecture & database schema design | Team | W3-4 | bar: PHASE 1 – Project Conception & Design Week 3 to PHASE 1 – Project Conception & Design Week 4
1.4 | UI/UX wireframes & prototype | Team | W4-5 | bar: PHASE 1 – Project Conception & Design Week 4 to PHASE 1 – Project Conception & Design Week 5
1.5 | Presentation I – proposal & design | Team | W5 | bar: PHASE 1 – Project Conception & Design Week 5
Phase 2: Development, Integration & Delivery
2.1 | Firebase setup & data modeling | Team | W5-6 | bar: PHASE 1 – Project Conception & Design Week 5 to PHASE 1 – Project Conception & Design Week 6
2.2 | Flask backend & REST API development | Team | W7-9 | bar: PHASE 1 – Project Conception & Design Week 7 to PHASE 2 – Development, Integration & Delivery Week 9
2.3 | Flutter app – login, dashboard, QR module | Team | W8-11 | bar: PHASE 1 – Project Conception & Design Week 8 to PHASE 2 – Development, Integration & Delivery Week 11
2.4 | Token issuance & redemption logic | Team | W10-12 | bar: PHASE 2 – Development, Integration & Delivery Week 10 to PHASE 2 – Development, Integration & Delivery Week 12
2.5 | Integration & end-to-end testing | Team | W12-14 | bar: PHASE 2 – Development, Integration & Delivery Week 12 to PHASE 2 – Development, Integration & Delivery Week 14
2.6 | Bug fixing & performance optimization | Team | W14-15 | bar: PHASE 2 – Development, Integration & Delivery Week 14 to PHASE 2 – Development, Integration & Delivery Week 15
2.7 | Final report, documentation & Presentation II | Team | W16-17 | bar: PHASE 2 – Development, Integration & Delivery Week 16 to PHASE 2 – Development, Integration & Delivery Week 17
LEGEND | Phase 1 Tasks |  | Phase 2 Backend | PHASE 1 – Project Conception & Design Week 2: Flutter Development; PHASE 1 – Project Conception & Design Week 4: Testing & QA; PHASE 1 – Project Conception & Design Week 6: Presentations; PHASE 1 – Project Conception & Design Week 8: Documentation